## Road-Map
March | April | May
Milestones and Dates | Milestones and Dates | Milestones and Dates
Sprint 1 (Mar 2 - Mar 13)
Sprint 2 (Mar 16 - Mar 27)
Sprint 3 (Mar 30 - Apr 10)
Sprint 1 (Mar 2 - Mar 13)
Sprint 4 (Apr 13 - Apr 24)
Sprint 3 (Mar 30 - Apr 10)
Sprint 1 (Mar 2 - Mar 13)
Sprint 4 (Apr 13 - Apr 24)
Sprint 5 (Apr 27 - May 8)
Sprint 1 (Mar 2 - Mar 13)
Sprint 6 (May 11 - May 22)
S1
E1
S2
S3
S4
S10
S5
S6
S7
S8
E2
E3
S9
E4
S11
E5
S12
Product Deployement (Apr 20)
Go Live
Final Testing
Final Sprint
S13
S14
S13

## Product Backlog Tasks
No. | Sprint # | Sprint + Day | Sprint+Task+Day | Task # | Sprint Task Number | S Number + Task | Epic | Story | Tasks | Priority | Status | Budget for Sprint | Budget for the task | Story Point for Sprint | Story Point for Task | Completion | Total Tasks | Sprint Start Date | Sprint End Date | Hours | Start Hour | End Hour | Add weekend | Task Start Date | Task End Date | Day | Task Completed Date | Task Started Date | Task Not Started Date | Start Hour | End Hour | Add weekend | Scheduled Task Start Date | Scheduled Task End Date | Task Completed Date | Task Started Date | Task Not Started Date | RM Discription | RM impact | RM Probobility | RM Severity (Loss in days)
S01 | 1 | 11 | 1S011 | 1 | 1 | S011 | Manager Application | As a manager, I want to add loads to the system so that I can organize daily operations. | Create Jobs | High | Completed | 25000 | 2820.5128 | 22 | 5.5 |  | 4 | 2020-03-02 | 2020-03-13 | 8 | 1 | 9 |  | 2020-03-02 | 2020-03-03 | 1 | 2020-03-03 | 2020-03-02 |  | 1 | 9 |  | 2020-03-02 | 2020-03-03 03:00 | 2020-03-03 03:00 | 2020-03-02 |  | Bad or missing data in the source system may impact the result of the missing data. | 4 | 2 | 8
S01 | 1 | 12 | 1S012 | 2 | 2 | S012 | Manager Application | As a manager, I want to add loads to the system so that I can organize daily operations. | Load Info Screen Design | High | Completed | 25000 | 2820.5128 | 22 | 5.5 |  | 4 | 2020-03-02 | 2020-03-13 | 8 | 10 | 18 |  | 2020-03-03 | 2020-03-04 | 2 | 2020-03-04 | 2020-03-03 |  | 10 | 18 |  | 2020-03-03 06:00 | 2020-03-04 06:00 | 2020-03-04 06:00 | 2020-03-03 06:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S01 | 1 | 13 | 1S013 | 3 | 3 | S013 | Manager Application | As a manager, I want to add loads to the system so that I can organize daily operations. | Customer info Screen Design | High | Completed | 25000 | 2820.5128 | 22 | 5.5 |  | 4 | 2020-03-02 | 2020-03-13 | 8 | 19 | 27 |  | 2020-03-04 | 2020-03-05 | 3 | 2020-03-05 | 2020-03-04 |  | 19 | 27 |  | 2020-03-04 09:00 | 2020-03-05 09:00 | 2020-03-05 09:00 | 2020-03-04 09:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S01 | 1 | 14 | 1S014 | 4 | 4 | S014 | Manager Application | As a manager, I want to add loads to the system so that I can organize daily operations. | Submit info Button | High | Completed | 25000 | 2820.5128 | 22 | 5.5 |  | 4 | 2020-03-02 | 2020-03-13 | 8 | 28 | 36 |  | 2020-03-05 | 2020-03-06 | 4 | 2020-03-06 | 2020-03-05 |  | 28 | 36 |  | 2020-03-05 12:00 | 2020-03-06 12:00 | 2020-03-06 12:00 | 2020-03-05 12:00 |  | Bad or missing code may impact the result of the missing data. | 2 | 4 | 8
S02 | 1 | 15 | 1S025 | 1 | 5 | S021 | Manager Application | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Despatch Screen Design | High | Completed | 25000 | 2666.6667 | 26 | 5.2 |  | 5 | 2020-03-02 | 2020-03-13 | 8 | 37 | 45 |  | 2020-03-06 | 2020-03-07 | 5 | 2020-03-07 | 2020-03-06 |  | 37 | 45 |  | 2020-03-06 15:00 | 2020-03-07 15:00 | 2020-03-07 15:00 | 2020-03-06 15:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S02 | 1 | 16 | 1S026 | 2 | 6 | S022 | Manager Application | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Access Asset Screen | High | Completed | 25000 | 2666.6667 | 26 | 5.2 |  | 5 | 2020-03-02 | 2020-03-13 | 8 | 62 | 70 | 16 | 2020-03-09 | 2020-03-10 | 6 | 2020-03-10 | 2020-03-09 |  | 62 | 70 | 16 | 2020-03-09 18:00 | 2020-03-10 18:00 | 2020-03-10 18:00 | 2020-03-09 18:00 |  | Bad or missing data in the source system may impact the result of the report. | 3 | 4 | 12
S02 | 1 | 17 | 1S027 | 3 | 7 | S023 | Manager Application | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Access Jops List Design | High | Completed | 25000 | 2666.6667 | 26 | 5.2 |  | 5 | 2020-03-02 | 2020-03-13 | 8 | 71 | 79 |  | 2020-03-10 | 2020-03-11 | 7 | 2020-03-11 | 2020-03-10 |  | 71 | 79 |  | 2020-03-10 21:00 | 2020-03-11 21:00 | 2020-03-11 21:00 | 2020-03-10 21:00 |  | Bad or missing data in the source system may impact the result of the report. | 3 | 4 | 12
S02 | 1 | 18 | 1S028 | 4 | 8 | S024 | Manager Application | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Select Driver Screen Design | High | Completed | 25000 | 2666.6667 | 26 | 5.2 |  | 5 | 2020-03-02 | 2020-03-13 | 8 | 80 | 88 |  | 2020-03-12 | 2020-03-13 | 8 | 2020-03-13 | 2020-03-12 |  | 80 | 88 |  | 2020-03-12 | 2020-03-13 | 2020-03-13 | 2020-03-12 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S02 | 1 | 19 | 1S029 | 5 | 9 | S025 | Manager Application | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Submit info Button | High | Completed | 25000 | 2666.6667 | 26 | 5.2 |  | 5 | 2020-03-02 | 2020-03-13 | 8 | 89 | 97 |  | 2020-03-13 | 2020-03-13 | 9 | 2020-03-16 | 2020-03-16 |  | 89 | 97 |  | 2020-03-13 03:00 | 2020-03-13 | 2020-03-13 | 2020-03-13 03:00 |  | Bad or missing code may impact the result of the missing data. | 2 | 4 | 8
S03 | 2 | 21 | 2S031 | 1 | 1 | S031 | Manager Application | As a manger, I want to track the load status and location so that I can make sure the services are performed as promised. | Load Status Screen Design | High | Completed | 25000 | 2179.4872 | 17 | 4.25 |  | 4 | 2020-03-16 | 2020-03-27 | 6 | 1 | 7 |  | 2020-03-16 | 2020-03-16 | 1 | 2020-03-17 | 2020-03-16 |  | 1 | 7 |  | 2020-03-16 | 2020-03-16 | 2020-03-16 | 2020-03-16 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S03 | 2 | 21 | 2S031 | 2 | 2 | S032 | Manager Application | As a manger, I want to track the load status and location so that I can make sure the services are performed as promised. | Job Status Screen Design | High | Completed | 25000 | 2179.4872 | 17 | 4.25 |  | 4 | 2020-03-16 | 2020-03-27 | 6 | 8 | 14 |  | 2020-03-16 | 2020-03-17 | 1 | 2020-03-17 | 2020-03-16 |  | 8 | 14 |  | 2020-03-16 | 2020-03-17 18:00 | 2020-03-17 18:00 | 2020-03-16 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S03 | 2 | 22 | 2S032 | 3 | 3 | S033 | Manager Application | As a manger, I want to track the load status and location so that I can make sure the services are performed as promised. | Asset Location Screen Design | High | Completed | 25000 | 2179.4872 | 17 | 4.25 |  | 4 | 2020-03-16 | 2020-03-27 | 6 | 15 | 21 |  | 2020-03-17 | 2020-03-18 | 2 | 2020-03-18 | 2020-03-17 |  | 15 | 21 |  | 2020-03-17 21:00 | 2020-03-18 15:00 | 2020-03-18 15:00 | 2020-03-17 21:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S03 | 2 | 23 | 2S033 | 4 | 4 | S034 | Manager Application | As a manger, I want to track the load status and location so that I can make sure the services are performed as promised. | Implement Inspection Report | High | Completed | 25000 | 2179.4872 | 17 | 4.25 |  | 4 | 2020-03-16 | 2020-03-27 | 6 | 22 | 28 |  | 2020-03-18 | 2020-03-19 | 3 | 2020-03-19 | 2020-03-18 |  | 22 | 28 |  | 2020-03-18 18:00 | 2020-03-19 12:00 | 2020-03-19 12:00 | 2020-03-18 18:00 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 2 | 8
S04 | 3 | 31 | 3S041 | 1 | 1 | S041 | Manager Application | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Invoice Form Design | High | Completed | 25000 | 1846.1538 | 18 | 3.6 |  | 5 | 2020-03-30 | 2020-04-12 | 5 | 1 | 6 |  | 2020-03-30 | 2020-03-30 | 1 | 2020-03-31 | 2020-03-30 |  | 1 | 6 |  | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 |  | Bad or missing data/design form integrating may cause system error or data error. | 5 | 2 | 10
S04 | 3 | 31 | 3S041 | 2 | 2 | S042 | Manager Application | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Retrive Jop/Order Info | High | Completed | 25000 | 1846.1538 | 18 | 3.6 |  | 5 | 2020-03-30 | 2020-04-12 | 5 | 7 | 12 |  | 2020-03-30 | 2020-03-31 | 1 | 2020-03-31 | 2020-03-30 |  | 7 | 12 |  | 2020-03-30 | 2020-03-31 12:00 | 2020-03-31 12:00 | 2020-03-30 |  | Bad or missing data/design form integrating may cause system error or data error. | 5 | 3 | 15
S04 | 3 | 32 | 3S042 | 3 | 3 | S043 | Manager Application | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Retrive Additional Expences | High | Completed | 25000 | 1846.1538 | 18 | 3.6 |  | 5 | 2020-03-30 | 2020-04-12 | 5 | 13 | 18 |  | 2020-03-31 | 2020-04-01 | 2 | 2020-04-01 | 2020-03-31 |  | 13 | 18 |  | 2020-03-31 15:00 | 2020-04-01 06:00 | 2020-04-01 06:00 | 2020-03-31 15:00 |  | Bad or missing data/design form integrating may cause system error or data error. | 4 | 2 | 8
S04 | 3 | 33 | 3S043 | 4 | 4 | S044 | Manager Application | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Generate Invoice | High | Completed | 25000 | 1846.1538 | 18 | 3.6 |  | 5 | 2020-03-30 | 2020-04-12 | 5 | 19 | 24 |  | 2020-04-01 | 2020-04-02 | 3 | 2020-04-02 | 2020-04-01 |  | 19 | 24 |  | 2020-04-01 09:00 | 2020-04-02 | 2020-04-02 | 2020-04-01 09:00 |  | Bad or missing data/design form integrating may cause system error or data error. | 5 | 4 | 20
S04 | 3 | 34 | 3S044 | 5 | 5 | S045 | Manager Application | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Send Invoice To the Customer | High | Completed | 25000 | 1846.1538 | 18 | 3.6 |  | 5 | 2020-03-30 | 2020-04-12 | 5 | 25 | 30 |  | 2020-04-02 | 2020-04-02 | 4 | 2020-04-03 | 2020-04-02 |  | 25 | 30 |  | 2020-04-02 03:00 | 2020-04-02 18:00 | 2020-04-02 18:00 | 2020-04-02 03:00 |  | Bad or missing data/design form integrating may cause system error or data error. | 3 | 4 | 12
S05 | 3 | 34 | 3S054 | 1 | 6 | S051 | Manager Application | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Create Report Screen | High | Completed | 25000 | 2564.1026 | 25 | 5 |  | 5 | 2020-03-30 | 2020-04-12 | 8 | 31 | 39 |  | 2020-04-02 | 2020-04-03 | 4 | 2020-04-03 | 2020-04-02 |  | 31 | 39 |  | 2020-04-02 21:00 | 2020-04-03 21:00 | 2020-04-03 21:00 | 2020-04-02 21:00 |  | Bad or missing data/design form integrating may cause system error or data error. | 4 | 2 | 8
S05 | 4 | 41 | 4S051 | 2 | 7 | S052 | Manager Application | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Create Period Selection Screen | High | Completed | 25000 | 2564.1026 | 25 | 5 |  | 5 | 2020-04-13 | 2020-04-24 | 13 | 1 | 14 |  | 2020-04-13 | 2020-04-14 | 1 | 2020-04-13 | 2020-04-13 |  | 1 | 14 |  | 2020-04-13 | 2020-04-14 18:00 | 2020-04-14 18:00 | 2020-04-13 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 4 | 16
S05 | 4 | 42 | 4S052 | 3 | 8 | S053 | Manager Application | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Create Report Data Selection Screen | High | Completed | 25000 | 2564.1026 | 25 | 5 |  | 5 | 2020-04-13 | 2020-04-24 | 13 | 15 | 28 |  | 2020-04-14 | 2020-04-16 | 2 | 2020-04-14 | 2020-04-14 |  | 15 | 28 |  | 2020-04-14 21:00 | 2020-04-16 12:00 | 2020-04-16 12:00 | 2020-04-14 21:00 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 2 | 8
S05 | 4 | 43 | 4S053 | 4 | 9 | S054 | Manager Application | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Export Report Option | High | Completed | 25000 | 2564.1026 | 25 | 5 |  | 5 | 2020-04-13 | 2020-04-24 | 13 | 29 | 42 |  | 2020-04-16 | 2020-04-18 | 3 | 2020-04-16 | 2020-04-16 |  | 29 | 42 |  | 2020-04-16 15:00 | 2020-04-18 06:00 | 2020-04-18 06:00 | 2020-04-16 15:00 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 2 | 8
S05 | 4 | 44 | 4S054 | 5 | 10 | S055 | Manager Application | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Save Report Template Option | High | Completed | 25000 | 2564.1026 | 25 | 5 |  | 5 | 2020-04-13 | 2020-04-24 | 13 | 43 | 56 |  | 2020-04-18 | 2020-04-20 | 4 | 2020-04-18 | 2020-04-18 |  | 43 | 56 |  | 2020-04-18 09:00 | 2020-04-20 | 2020-04-20 | 2020-04-18 09:00 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 2 | 8
S06 | 4 | 46 | 4S066 | 1 | 1 | S061 | Manager Application | As a manager, I want to generate payroll so that I can send paycheck to our drivers and report expenses correctly into the accounting system. | Greate Payroll Report | High | Completed | 25000 | 5384.6154 | 21 | 10.5 |  | 2 | 2020-04-13 | 2020-04-24 | 16 | 57 | 73 |  | 2020-04-20 | 2020-04-22 | 6 | 2020-04-20 | 2020-04-20 |  | 57 | 73 |  | 2020-04-20 03:00 | 2020-04-22 03:00 | 2020-04-22 03:00 | 2020-04-20 03:00 |  | Bad or missing data in the source system may impact the result of the report. | 4 | 2 | 8
S06 | 4 | 48 | 4S068 | 2 | 2 | S062 | Manager Application | As a manager, I want to generate payroll so that I can send paycheck to our drivers and report expenses correctly into the accounting system. | Submit Payroll Report | High | Completed | 25000 | 5384.6154 | 21 | 10.5 |  | 2 | 2020-04-13 | 2020-04-24 | 16 | 74 | 90 |  | 2020-04-22 | 2020-04-24 | 8 | 2020-04-22 | 2020-04-22 |  | 74 | 90 |  | 2020-04-22 06:00 | 2020-04-24 |  |  |  | Bad or missing code may impact the result of the missing data. | 4 | 4 | 16
S07 | 1 | 18 | 1S078 | 1 | 10 | S071 | Driver Application | As a driver, I want to receive detailed information about the load so that I can do plan my day for pickup loads. | Notification Designed for Despatch Jobs | High | Completed | 25000 | 4871.7949 | 19 | 9.5 |  | 2 | 2020-03-02 | 2020-03-13 | 14 | 114 | 128 | 16 | 2020-03-16 | 2020-03-13 | 8 | 2020-03-13 | 2020-03-16 |  | 107 | 121 | 16 | 2020-03-15 09:00 | 2020-03-13 | 2020-03-13 | 2020-03-15 09:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 3 | 9
S07 | 2 | 24 | 2S074 | 2 | 11 | S072 | Driver Application | As a driver, I want to receive detailed information about the load so that I can do plan my day for pickup loads. | Accept Jobs | High | Completed | 25000 | 4871.7949 | 19 | 9.5 |  | 2 | 2020-03-16 | 2020-03-29 | 7 | 29 | 36 |  | 2020-03-19 | 2020-03-20 | 4 | 2020-03-20 | 2020-03-19 |  | 122 | 129 |  | 2020-03-31 06:00 | 2020-03-29 | 2020-03-29 | 2020-03-31 06:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 4 | 1 | 4
S08 | 2 | 25 | 2S085 | 1 | 5 | S081 | Driver Application | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Design Inspection Screen | High | Completed | 25000 | 1435.8974 | 14 | 2.8 |  | 5 | 2020-03-16 | 2020-03-27 | 4 | 37 | 41 |  | 2020-03-20 | 2020-03-21 | 5 | 2020-03-23 | 2020-03-20 |  | 130 | 134 |  | 2020-04-01 06:00 | 2020-03-27 | 2020-03-27 | 2020-04-01 06:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 5 | 2 | 10
S08 | 2 | 26 | 2S086 | 2 | 6 | S082 | Driver Application | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Import Photo Screen Design | High | Completed | 25000 | 1435.8974 | 14 | 2.8 |  | 5 | 2020-03-16 | 2020-03-27 | 4 | 58 | 62 | 16 | 2020-03-23 | 2020-03-23 | 6 | 2020-03-24 | 2020-03-23 |  | 151 | 155 | 16 | 2020-04-03 21:00 | 2020-03-27 | 2020-03-27 | 2020-04-03 21:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S08 | 3 | 35 | 3S085 | 3 | 7 | S083 | Driver Application | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Access Camera Screen Design | High | Completed | 25000 | 1435.8974 | 14 | 2.8 |  | 5 | 2020-03-30 | 2020-04-12 | 4 | 56 | 60 | 16 | 2020-04-06 | 2020-04-06 | 5 | 2020-04-07 | 2020-04-06 |  | 172 | 176 | 16 | 2020-04-20 12:00 | 2020-04-12 | 2020-04-12 | 2020-04-20 12:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S08 | 3 | 35 | 3S085 | 4 | 8 | S084 | Driver Application | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Edit Image Screen Design | High | Completed | 25000 | 1435.8974 | 14 | 2.8 |  | 5 | 2020-03-30 | 2020-04-12 | 4 | 61 | 65 |  | 2020-04-06 | 2020-04-07 | 5 | 2020-04-07 | 2020-04-06 |  | 177 | 181 |  | 2020-04-21 03:00 | 2020-04-12 | 2020-04-12 | 2020-04-21 03:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S08 | 3 | 36 | 3S086 | 5 | 9 | S085 | Driver Application | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Submit Inspection Report Desgn | High | Completed | 25000 | 1435.8974 | 14 | 2.8 |  | 5 | 2020-03-30 | 2020-04-12 | 4 | 66 | 70 |  | 2020-04-07 | 2020-04-07 | 6 | 2020-04-08 | 2020-04-07 |  | 182 | 186 |  | 2020-04-21 18:00 | 2020-04-12 | 2020-04-12 | 2020-04-21 18:00 |  | Bad or missing code may impact the result of the missing data. | 4 | 4 | 16
S09 | 3 | 36 | 3S096 | 1 | 10 | S091 | Driver Application | As a driver, I want to submit incurred expenses (gas, toll, repair…) with the image of the receipt so that I can claim them back from the company. | Design Expence Screen Design | High | Completed | 25000 | 2564.1026 | 15 | 5 |  | 3 | 2020-03-30 | 2020-04-12 | 8 | 71 | 79 |  | 2020-04-07 | 2020-04-08 | 6 | 2020-04-08 | 2020-04-07 |  | 187 | 195 |  | 2020-04-22 09:00 | 2020-04-12 | 2020-04-12 | 2020-04-22 09:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S09 | 3 | 37 | 3S097 | 2 | 11 | S092 | Driver Application | As a driver, I want to submit incurred expenses (gas, toll, repair…) with the image of the receipt so that I can claim them back from the company. | Implement Scan Image Desgn | High | Completed | 25000 | 2564.1026 | 15 | 5 |  | 3 | 2020-03-30 | 2020-04-12 | 8 | 80 | 88 |  | 2020-04-09 | 2020-04-10 | 7 | 2020-04-10 | 2020-04-09 |  | 196 | 204 |  | 2020-04-23 12:00 | 2020-04-12 | 2020-04-12 | 2020-04-23 12:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 3 | 9
S09 | 3 | 38 | 3S098 | 3 | 12 | S093 | Driver Application | As a driver, I want to submit incurred expenses (gas, toll, repair…) with the image of the receipt so that I can claim them back from the company. | Assgn Expence to Spesific Job/Jobs | High | Completed | 25000 | 2564.1026 | 15 | 5 |  | 3 | 2020-03-30 | 2020-04-12 | 8 | 89 | 97 |  | 2020-04-10 | 2020-04-11 | 8 | 2020-04-11 | 2020-04-10 |  | 205 | 213 |  | 2020-04-24 15:00 | 2020-04-12 | 2020-04-12 |  | 2020-04-24 15:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 3 | 9
S10 | 4 | 410 | 4S1010 | 1 | 3 | S101 | Driver Application | As a driver, I want to confirm delivery, so that the system can generate invoice for the customer. | Job Complete Screen Design | High | Completed | 25000 | 2307.6923 | 18 | 4.5 |  | 4 | 2020-04-13 | 2020-04-24 | 7 | 91 | 98 |  | 2020-04-24 | 2020-04-24 | 10 | 2020-04-24 | 2020-04-24 |  | 214 | 221 |  | 2020-05-09 18:00 | 2020-04-24 |  |  | 2020-05-09 18:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S10 | 5 | 51 | 5S101 | 2 | 4 | S102 | Driver Application | As a driver, I want to confirm delivery, so that the system can generate invoice for the customer. | Deliver inspection Screen Design | High | Active | 25000 | 2307.6923 | 18 | 4.5 |  | 4 | 2020-04-27 | 2020-05-08 | 7 | 1 | 8 |  | 2020-04-13 | 2020-04-13 | 1 | 2020-04-13 | 2020-04-13 |  | 1 | 8 |  | 2020-04-27 | 2020-04-27 |  |  | 2020-04-27 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S10 | 5 | 52 | 5S102 | 3 | 5 | S103 | Driver Application | As a driver, I want to confirm delivery, so that the system can generate invoice for the customer. | Submit Delivery Complete | High | Active | 25000 | 2307.6923 | 18 | 4.5 |  | 4 | 2020-04-27 | 2020-05-08 | 7 | 9 | 16 |  | 2020-04-28 | 2020-04-29 | 2 |  |  | 2020-04-28 | 9 | 16 |  | 2020-04-28 03:00 | 2020-04-29 |  |  | 2020-04-28 03:00 | Bad or missing code may impact the result of the missing data. | 2 | 4 | 8
S11 | 2 | 26 | 2S116 | 1 | 12 | S111 | Customer Application | As a customer, I want to be able to see the inspection report and approve at the time of pickup so that I make sure my car is picked up as is. | Customer Access Screen Desgin | High | Completed | 25000 | 1923.0769 | 15 | 3.75 |  | 4 | 2020-03-16 | 2020-03-29 | 6 | 63 | 69 |  | 2020-03-23 | 2020-03-24 | 6 | 2020-03-24 | 2020-03-23 |  | 17 | 23 |  | 2020-03-18 03:00 | 2020-03-18 21:00 | 2020-03-18 21:00 | 2020-03-18 03:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S11 | 2 | 27 | 2S117 | 2 | 13 | S112 | Customer Application | As a customer, I want to be able to see the inspection report and approve at the time of pickup so that I make sure my car is picked up as is. | Inpection Access design | High | Completed | 25000 | 1923.0769 | 15 | 3.75 |  | 4 | 2020-03-16 | 2020-03-27 | 6 | 70 | 76 |  | 2020-03-24 | 2020-03-25 | 7 | 2020-03-25 | 2020-03-24 |  | 24 | 30 |  | 2020-03-19 | 2020-03-19 18:00 | 2020-03-19 18:00 | 2020-03-19 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S11 | 2 | 28 | 2S118 | 3 | 14 | S113 | Customer Application | As a customer, I want to be able to see the inspection report and approve at the time of pickup so that I make sure my car is picked up as is. | Accept Inspection | High | Completed | 25000 | 1923.0769 | 15 | 3.75 |  | 4 | 2020-03-16 | 2020-03-29 | 6 | 77 | 83 |  | 2020-03-25 | 2020-03-26 | 8 | 2020-03-26 | 2020-03-25 |  | 31 | 37 |  | 2020-03-19 21:00 | 2020-03-20 15:00 | 2020-03-20 15:00 | 2020-03-19 21:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S11 | 2 | 29 | 2S119 | 4 | 15 | S114 | Customer Application | As a customer, I want to be able to see the inspection report and approve at the time of pickup so that I make sure my car is picked up as is. | Reject Inspection | High | Completed | 25000 | 1923.0769 | 15 | 3.75 |  | 4 | 2020-03-16 | 2020-03-29 | 6 | 84 | 90 |  | 2020-03-26 | 2020-03-27 | 9 | 2020-03-27 | 2020-03-26 |  | 38 | 44 |  | 2020-03-20 18:00 | 2020-03-21 12:00 | 2020-03-21 12:00 | 2020-03-20 18:00 |  | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S12 | 5 | 53 | 5S123 | 1 | 6 | S121 | Customer Application | As a customer, I want to check the load status and location and estimated arrival, so that I know when my car will be delivered to the new location. | Load Status Screen Design | High | Active | 25000 | 5128.2051 | 20 | 10 |  | 2 | 2020-04-27 | 2020-05-08 | 15 | 17 | 32 |  | 2020-04-29 | 2020-05-01 | 3 |  |  | 2020-04-29 | 45 | 60 |  | 2020-05-02 15:00 | 2020-05-04 12:00 |  |  | 2020-05-02 15:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S12 | 5 | 54 | 5S124 | 2 | 7 | S122 | Customer Application | As a customer, I want to check the load status and location and estimated arrival, so that I know when my car will be delivered to the new location. | Load map View Screen Desgin | High | Active | 25000 | 5128.2051 | 20 | 10 |  | 2 | 2020-04-27 | 2020-05-08 | 15 | 57 | 72 | 24 | 2020-05-04 | 2020-05-06 | 4 |  |  | 2020-05-04 | 85 | 100 | 24 | 2020-05-07 15:00 | 2020-05-08 |  |  | 2020-05-07 15:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S13 | 6 | 61 | 6S131 | 1 | 1 | S131 | Web Server | As an user, I want to be able to use the system via web browser so that I don’t have to have smart device. | User Access Screen Design | High | Active | 25000 | 5470.0855 | 32 | 10.6667 |  | 3 | 2020-05-11 | 2020-05-22 | 16 | 1 | 17 |  | 2020-05-11 | 2020-05-13 | 1 |  |  | 2020-05-11 | 1 | 17 |  | 2020-05-11 | 2020-05-13 03:00 |  |  | 2020-05-11 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S13 | 6 | 63 | 6S133 | 2 | 2 | S132 | Web Server | As an user, I want to be able to use the system via web browser so that I don’t have to have smart device. | Driver Screen Design | High | Active | 25000 | 5470.0855 | 32 | 10.6667 |  | 3 | 2020-05-11 | 2020-05-22 | 16 | 18 | 34 |  | 2020-05-13 | 2020-05-15 | 3 |  |  | 2020-05-13 | 18 | 34 |  | 2020-05-13 06:00 | 2020-05-15 06:00 |  |  | 2020-05-13 06:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S13 | 6 | 66 | 6S136 | 3 | 3 | S133 | Web Server | As an user, I want to be able to use the system via web browser so that I don’t have to have smart device. | Manager Screen Design | High | Active | 25000 | 5470.0855 | 32 | 10.6667 |  | 3 | 2020-05-11 | 2020-05-22 | 16 | 35 | 51 |  | 2020-05-15 | 2020-05-17 | 6 |  |  | 2020-05-15 | 35 | 51 |  | 2020-05-15 09:00 | 2020-05-17 09:00 |  |  | 2020-05-15 09:00 | Bad or missing Code or section in the source system may impact the result of the missing data. | 3 | 2 | 6
S14 | 5 | 55 | 5S145 | 1 | 1 | S141 | Database | As an user, I want to save all relevent data and information to a database so that I can generate reports for business operations. | Database Tables Design | High | Active | 25000 | 8974.359 | 35 | 17.5 |  | 2 | 2020-04-27 | 2020-05-08 | 26 | 73 | 99 |  | 2020-05-06 | 2020-05-08 | 5 |  |  | 2020-05-06 | 52 | 78 |  | 2020-05-03 12:00 | 2020-05-06 18:00 |  |  | 2020-05-03 12:00 | Bad or Missing table may impact the system | 5 | 5 | 25
S14 | 5 | 56 | 5S146 | 2 | 2 | S142 | Database | As an user, I want to save all relevent data and information to a database so that I can generate reports for business operations. | Database User Access Design | High | Active | 25000 | 8974.359 | 35 | 17.5 |  | 2 | 2020-04-27 | 2020-05-08 | 26 | 116 | 142 | 16 | 2020-05-11 | 2020-05-08 | 6 |  |  | 2020-05-11 | 95 | 121 | 16 | 2020-05-08 21:00 | 2020-05-08 |  |  | 2020-05-08 21:00 | Bad or Missing data may resault system to not run | 5 | 5 | 25
Formulas:
Task Started Date = [Task Start Date]
Task Started Date = IF([Scheduled Task Start Date]<TODAY(),[Scheduled Task Start Date],"")
Scheduled Task Start Date = IF([Start Hour]<9,[Sprint Start Date],[Sprint Start Date]+[Start Hour]/8)
Scheduled Task End Date = IF([Sprint End Date]>IF([End Hour]<9,[Sprint Start Date],[Sprint Start Date]+[End Hour]/8),IF([End Hour]<9,[Sprint Start Date],[Sprint Start Date]+[End Hour]/8),[Sprint End Date])
Task Completed Date = IF([Scheduled Task End Date]<TODAY(),[Scheduled Task End Date],"")
Task Not Started Date = IF([Scheduled Task Start Date]>TODAY(),[Scheduled Task Start Date],"")

## CFD
Date | Completed for the day | Completed | Started this day | Accumulated started | Started | Not Started
|  | 0 | 0
2020-03-02 | 0 | 0 | 5.5 | 5.5 | 5.5 | 287
2020-03-03 | 5.5 | 5.5 | 11 | 16.5 | 11 | 276
2020-03-04 | 5.5 | 11 | 16.5 | 22 | 11 | 270.5
2020-03-05 | 5.5 | 16.5 | 22 | 27.5 | 11 | 265
2020-03-06 | 5.5 | 22 | 27.2 | 32.7 | 10.7 | 259.8
2020-03-09 | 0 | 22 | 32.4 | 32.4 | 10.4 | 260.1
2020-03-11 | 5.2 | 27.2 | 32.4 | 37.6 | 10.4 | 254.9
2020-03-12 | 0 | 27.2 | 37.6 | 37.6 | 10.4 | 254.9
2020-03-13 | 14.7 | 41.9 | 37.6 | 52.3 | 10.4 | 240.2
2020-03-16 | 5.2 | 47.1 | 60.8 | 66 | 18.9 | 226.5
2020-03-17 | 8.5 | 55.6 | 65.05 | 73.55 | 17.95 | 218.95
2020-03-18 | 4.25 | 59.85 | 69.3 | 73.55 | 13.7 | 218.95
2020-03-19 | 4.25 | 64.1 | 78.8 | 83.05 | 18.95 | 209.45
2020-03-20 | 9.5 | 73.6 | 81.6 | 91.1 | 17.5 | 201.4
2020-03-23 | 2.8 | 76.4 | 88.15 | 90.95 | 14.55 | 201.55
2020-03-24 | 6.55 | 82.95 | 91.9 | 98.45 | 15.5 | 194.05
2020-03-25 | 3.75 | 86.7 | 95.65 | 99.4 | 12.7 | 193.1
2020-03-26 | 3.75 | 90.45 | 99.4 | 103.15 | 12.7 | 189.35
2020-03-27 | 3.75 | 94.2 | 99.4 | 103.15 | 8.95 | 189.35
2020-03-30 | 0 | 94.2 | 106.6 | 106.6 | 12.4 | 185.9
2020-03-31 | 7.2 | 101.4 | 110.2 | 117.4 | 16 | 175.1
2020-04-01 | 3.6 | 105 | 113.8 | 117.4 | 12.4 | 175.1
2020-04-02 | 3.6 | 108.6 | 122.4 | 126 | 17.4 | 166.5
2020-04-03 | 8.6 | 117.2 | 122.4 | 131 | 13.8 | 161.5
2020-04-06 | 0 | 117.2 | 128 | 128 | 10.8 | 164.5
2020-04-07 | 5.6 | 122.8 | 135.8 | 141.4 | 18.6 | 151.1
2020-04-08 | 7.8 | 130.6 | 135.8 | 143.6 | 13 | 148.9
2020-04-09 | 0 | 130.6 | 140.8 | 140.8 | 10.2 | 151.7
2020-04-10 | 5 | 135.6 | 145.8 | 150.8 | 15.2 | 141.7
2020-04-13 | 0 | 135.6 | 145.8 | 145.8 | 10.2 | 146.7
2020-04-14 | 5 | 140.6 | 150.8 | 155.8 | 15.2 | 136.7
2020-04-15 | 0 | 140.6 | 150.8 | 150.8 | 10.2 | 141.7
2020-04-16 | 10.5 | 151.1 | 161.3 | 171.8 | 20.7 | 120.7
2020-04-17 | 0 | 151.1 | 161.3 | 161.3 | 10.2 | 131.2
2020-04-20 | 4.5 | 155.6 | 165.8 | 170.3 | 14.7 | 122.2
2020-04-21 | 0 | 155.6 | 165.8 | 165.8 | 10.2 | 126.7
2020-04-22 | 0 | 155.6 | 165.8 | 165.8 | 10.2 | 126.7
2020-04-23 | 0 | 155.6 | 165.8 | 165.8 | 10.2 | 126.7
2020-04-24 | 9.5 | 165.1 | 175.3 | 184.8 | 19.7 | 107.7
2020-04-27 | 0 | 165.1 | 175.3 | 175.3 | 10.2 | 117.2
Instruction to create CFD:
Insert Chart
More column chart
Area
Stacked

## Risk
Date | Risk gone this day | Accumlate risk gone | Risk left
|  |  | 440 | Sprint | End Date | Risks Exposure (Days)
2020-03-02 | 0 | 0 | 440 | 1 | 2020-03-13 | 365
2020-03-03 | 8 | 8 | 432 | 2 | 2020-03-27 | 266
2020-03-04 | 6 | 14 | 426 | 3 | 2020-04-13 | 223
2020-03-05 | 6 | 20 | 420 | 4 | 2020-04-24 | 165
2020-03-06 | 8 | 28 | 412 | 5 | 2020-05-08 | 153
2020-03-09 | 12 | 40 | 400 | 6 | 2020-05-22 | 153
2020-03-10 | 0 | 40 | 400
2020-03-11 | 15 | 55 | 385
2020-03-12 | 8 | 63 | 377
2020-03-13 | 12 | 75 | 365
2020-03-16 | 4 | 79 | 361
2020-03-17 | 10 | 89 | 351
2020-03-18 | 12 | 101 | 339
2020-03-19 | 6 | 107 | 333
2020-03-20 | 6 | 113 | 327
2020-03-23 | 25 | 138 | 302
2020-03-24 | 8 | 146 | 294
2020-03-25 | 20 | 166 | 274
2020-03-26 | 0 | 166 | 274
2020-03-27 | 8 | 174 | 266
2020-03-30 | 0 | 174 | 266
2020-03-31 | 0 | 174 | 266
2020-04-01 | 20 | 194 | 246
2020-04-02 | 0 | 194 | 246
2020-04-03 | 0 | 194 | 246
2020-04-06 | 6 | 200 | 240
2020-04-07 | 0 | 200 | 240
2020-04-08 | 0 | 200 | 240
2020-04-09 | 8 | 208 | 232
2020-04-10 | 0 | 208 | 232
2020-04-13 | 9 | 217 | 223
2020-04-14 | 22 | 239 | 201
2020-04-15 | 0 | 239 | 201
2020-04-16 | 16 | 255 | 185
2020-04-17 | 0 | 255 | 185
2020-04-20 | 6 | 261 | 179
2020-04-21 | 8 | 269 | 171
2020-04-22 | 6 | 275 | 165
2020-04-23 | 0 | 275 | 165
2020-04-24 | 0 | 275 | 165
2020-04-27 | 0 | 275 | 165
2020-04-28 | 0 | 275 | 165
2020-04-29 | 12 | 287 | 153
2020-04-30 | 0 | 287 | 153
2020-05-01 | 0 | 287 | 153
2020-05-04 | 0 | 287 | 153
2020-05-05 | 0 | 287 | 153
2020-05-06 | 0 | 287 | 153
2020-05-07 | 0 | 287 | 153
2020-05-08 | 0 | 287 | 153
2020-05-11 | 0 | 287 | 153
2020-05-12 | 0 | 287 | 153
2020-05-13 | 0 | 287 | 153
2020-05-14 | 0 | 287 | 153
2020-05-15 | 0 | 287 | 153
2020-05-18 | 0 | 287 | 153
2020-05-19 | 0 | 287 | 153
2020-05-20 | 0 | 287 | 153
2020-05-21 | 0 | 287 | 153
2020-05-22 | 0 | 287 | 153
Instruction to create CFD:
Insert Chart
More column chart
Area
Stacked

## DOD
Sprint DOD
Code peer-reviewed
Acceptance criteria met
All test cases for user stories passed
Integration tests passed
Documentation updated
Pre-production app run on top 5 browsers
Pre-prodution app run on top 3 mobile devices
System-level NFR (performance) is tested and passed
peer review
Acceptance criteria
Intergration
User stories
Documentation
Performance
APPROVAL
TEST
DEVELOP
Browsers
Mobile devices

## Package 5
Team Burn Rate
Sprint | 0 | 1 | 2 | 3 | 4 | 5 | 6
Ideal | 0 | 57.5 | 104.6 | 151 | 196.5 | 260.5 | 292.5
Project Scope | 293 | 293 | 293 | 293 | 293 | 293 | 293
Completion | 0 | 37.375 | 72.174 | 107.21 | 159.165 | 239.66 | 292.5
Completion% |  | 65% | 69% | 71% | 81% | 92% | 100%
Sprint | 0 | 1 | 2 | 3 | 4 | 5 | 6
Ideal Effort | 293 | 235.5 | 188.4 | 142 | 96.5 | 32.5 | 0.5
Actual Effort | 293 | 255.625 | 220.826 | 185.79 | 133.835 | 53.34 | 0.5
Sprint | 0 | 1 | 2 | 3 | 4 | 5 | 6
Sprint Hours | 0 | 86 | 63 | 69 | 91 | 96 | 48
Planned Burn Rate | 0 | 8.6 | 6.3 | 6.9 | 9.1 | 9.6 | 4.8
User Story | S01 | S02 | S03 | S04 | S05 | S06 | S07 | S08 | S09 | S10 | S11 | S12 | S13 | S14
User Story Hours | 32 | 40 | 24 | 25 | 60 | 32 | 21 | 20 | 24 | 21 | 24 | 30 | 48 | 52
Actual Hours | 35.2 | 44 | 26.4 | 27.5 | 66 | 35.2 | 23.1 | 22 | 26.4 | 23.1 | 26.4 | 33 | 52.8 | 57.2
Total Sprint Days | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Actual Burn Rate | 3.52 | 4.4 | 2.64 | 2.75 | 6.6 | 3.52 | 2.31 | 2.2 | 2.64 | 2.31 | 2.64 | 3.3 | 5.28 | 5.72
Resource Utilization
Sptint Start Date | S02: 1900-01-03; S03: 1900-01-03; S04: 1900-01-04; S05: 1900-01-04; S06: 1900-01-03; S07: 1900-01-02
Sptint End Date | S02: 2020-03-02; S03: 2020-03-16; S04: 2020-03-30; S05: 2020-04-13; S06: 2020-04-27; S07: 2020-05-11
Sprint | S01: 0; S02: 1; S03: 2; S04: 3; S05: 4; S06: 5; S07: 6; S14: Sprint: | 4
Planned Sprint Hours | S01: 0; S02: 86; S03: 63; S04: 69; S05: 91; S06: 96; S07: 48; S14: Planned burn rate: | 9.1
Actual Hours | S01: 0; S02: 98.9; S03: 72.45; S04: 79.35; S05: 83.72; S14: Actual burn rate: | 10.465
Sprint days | S01: 0; S02: 10; S03: 10; S04: 10; S05: 10
Days Used | S01: 0; S02: 10; S03: 10; S04: 10; S05: 8
| S14: Sprint: | 4
| S13: A; S14: total hours of all team: | 83.72
| S14: Cengiz: | 75% | 6 h/day
| S14: Chau: | 50% | 4h/day
| S13: B; S14: team: |  | 10h/day
| S13: A/B; S14: Days used for this sprint: |  | 8.372
Day 8?
Release Velocity
Sptint Start Date | S02: 2020-03-02; S03: 2020-03-16; S04: 2020-03-30; S05: 2020-04-13; S06: 2020-04-27; S07: 2020-05-11
Sptint End Date | S02: 2020-03-13; S03: 2020-03-27; S04: 2020-04-12; S05: 2020-04-24; S06: 2020-05-08; S07: 2020-05-22
Sprint | S01: 0; S02: 1; S03: 2; S04: 3; S05: 4; S06: 5; S07: 6; S14: Sprint: | 4
Story Point Completed | S02: 57.5; S03: 47.1; S04: 46.4; S05: 36.4; S14: Total Story points completed: | 187.4
Total Story Points Completed | S02: 57.5; S03: 104.6; S04: 151; S05: 187.4; S14: Velocity: | 46.85
Velocity | S02: 57.5; S03: 52.3; S04: 50.3333; S05: 46.85; S14: Release velocity: | 281.1
Release Velocity | S02: 345; S03: 313.8; S04: 302; S05: 281.1
Earned Value
Total Story Point: | S01: 292.5
Total Budget: | S01: 150000
Total Duration: | S01: 6 Sprint
Sptint Start Date | S02: 0; S03: 0; S04: 0; S05: 0; S06: 0; S07: 0
Sptint End Date | S02: 1900-01-03; S03: 1900-01-03; S04: 1900-01-04; S05: 1900-01-04; S06: 1900-01-03; S07: 1900-01-02
Sprint | S01: 0; S02: 1; S03: 2; S04: 3; S05: 4; S06: 5; S07: 6
Ideal % Complete | S01: 0; S02: 16.67%; S03: 33.33%; S04: 50%; S05: 66.67%
Total story point completed this sprint: | S02: 5750%; S03: 4710%; S04: 4640%; S05: 4550%
Actual % Complete | S01: 0; S02: 19.66%; S03: 35.76%; S04: 51.62%; S05: 67.18%
Budget for sprint | S01: 0; S02: 25000; S03: 25000; S04: 25000; S05: 25000
Budget Used | S01: 0; S02: 25000; S03: 50000; S04: 75000; S05: 95000
Budgeted Used: | S01: 0; S02: 16.67%; S03: 33.33%; S04: 50%; S05: 63.33%

## Product Backlog
No. | Sprint # | Epic | Story | Type | Complete Work | Work Done | Work in progress | Planned Start Date | Planned End Date
E1 |  | Manager Application |  | Epic | 129 | 65 | 129
S01 | 1 | 1 | As a manager, I want to add loads to the system so that I can organize daily operations. | Story | 22 | 22 | 22 | 2020-03-02 | 2020-03-13
S02 | 1 | 5 | As a manager, I want to be able to dispatch drivers with load so that I can communicate with drivers with detail information. | Story | 26 | 26 | 26 | 2020-03-02 | 2020-03-13
S03 | 2 | 1 | As a manger, I want to track the load status and location so that I can make sure the services are performed as promised. | Story | 17 | 17 | 17 | 2020-03-16 | 2020-03-27
S04 | 3 | 1 | As a manager, I want to generate invoice so that I can recognize the transaction in accounting and bill the customer as soon possible. | Story | 18 |  | 18 | 2020-04-13 | 2020-04-24
S05 | 3 | 6 | As a manger, I want to generate income report from any period revenues and expenses so that I can anaylyze the performance of our business. | Story | 25 |  | 25 | 2020-04-13 | 2020-04-24
S06 | 4 | 1 | As a manager, I want to generate payroll so that I can send paycheck to our drivers and report expenses correctly into the accounting system. | Story | 21 |  | 21 | 2020-04-27 | 2020-05-08
E2 | 0 | Driver Application |  | Epic | 0 | 0 | 0
S07 | 1 | 10 | As a driver, I want to receive detailed information about the load so that I can do plan my day for pickup loads. | Story | 19 | 19 | 19 | 2020-03-02 | 2020-03-13
S08 | 2 | 5 | As a driver, I want to take image of the car so that I can do inspection at the pickup location. | Story | 14 | 14 | 14 | 2020-03-16 | 2020-03-27
S09 | 2 | 10 | As a driver, I want to submit incurred expenses (gas, toll, repair…) with the image of the receipt so that I can claim them back from the company. | Story | 15 | 15 | 15 | 2020-03-16 | 2020-03-27
S10 | 4 | 3 | As a driver, I want to confirm delivery, so that the system can generate invoice for the customer. |  | 13.5 |  |  | 2020-04-27 | 2020-05-08
E3 | 0 | Customer Application |  | Epic | 0 | 0 | 0
S11 | 1 | 12 | As a customer, I want to be able to see the inspection report and approve at the time of pickup so that I make sure my car is picked up as is. | Story | 15 | 15 | 15 | 2020-03-02 | 2020-03-13
S12 | 4 | 6 | As a customer, I want to check the load status and location and estimated arrival, so that I know when my car will be delivered to the new location. | Story | 20 |  |  | 2020-04-27 | 2020-05-08
E4 |  | Web Server |  | Epic | 0 | 0 | 0
S13 | 6 | 1 | As an user, I want to be able to use the system via web browser so that I don’t have to have smart device. | Story | 32 |  |  | 2020-05-11 | 2020-05-22
E5 |  | Database |  | Epic | 0 | 0 | 0
S14 | 5 | 1 | As an user, I want to save all relevent data and information to a database so that I can generate reports for business operations. | Story | 35 |  |  | 2020-04-27 | 2020-05-08
Formulas:
Planned End Date = [Planned Start Date]+11

## Sprint Backlog
No. | User Story | Task ID | Tasks | Priority | Status | Hours | Story Points | Task# | Day | Sprint# | Task#
|  |  | 1 | [6 empty] | 1 | S01 | S02 | S07
S01 | S011 | S011 | Create Jobs | High | Completed | 8 | 5.5 | 1 | 1 | 2 | S07 | S08 | S11
S01 |  | S012 | Load Info Screen Design | High | Completed | 8 | 5.5 | 2 | 2 | 3 | S04 | S05 | S08 | S09
S01 |  | S013 | Customer info Screen Design | High | Completed | 8 | 5.5 | 3 | 3 | 4 | S05 | S06 | S10
S01 |  | S014 | Submit info Button | High | Completed | 8 | 5.5 | 4 | 4 | 5 | S10 | S12 | S14
S01 |  | S015 | [5 empty] | 5 | 4 | 6 | S13
S01 | S011 | S011 | Create Jobs | High | Completed | 8 | 5.5 | 1 | 5
S01 |  | S012 | Load Info Screen Design | High | Completed | 8 | 5.5 | 2 | 2
S01 |  | S013 | Customer info Screen Design | High | Completed | 8 | 5.5 | 3 | 3
S01 |  | S014 | Submit info Button | High | Completed | 8 | 5.5 | 4 | 4
S01 |  | S015 | [5 empty] | 5 | 4
S01 | S011 | S011 | Create Jobs | High | Completed | 8 | 5.5 | 1 | 6
S01 |  | S012 | Load Info Screen Design | High | Completed | 8 | 5.5 | 2 | 7
S01 |  | S013 | Customer info Screen Design | High | Completed | 8 | 5.5 | 3 | 4
S01 |  | S014 | Submit info Button | High | Completed | 8 | 5.5 | 4 | 8
S01 |  | S015 | [5 empty] | 5 | 8
S01 | S011 | S011 | Create Jobs | High | Completed | 8 | 5.5 | 1 | 9
S01 |  | S012 | Load Info Screen Design | High | Completed | 8 | 5.5 | 2 | 5
S01 |  | S013 | Customer info Screen Design | High | Completed | 8 | 5.5 | 3 | 7
S01 |  | S014 | Submit info Button | High | Completed | 8 | 5.5 | 4
S01 |  | S015 | [5 empty] | 5

## RoadMap
PROJECT Road Map
PROJECT DETAILS
DATE | MILESTONE | POSITION | BASELINE | Position Adjusted | Date adjusted | Milestone adjusted
2020-03-02 | Sprint 1 | 1 | 0 | 25 | 2020-03-25 | Sprint 1
2020-03-16 | Sprint 2 | 2 | 0 | -10 | 2020-04-01 | Sprint 2
2020-03-30 | Sprint 3 | 3 | 0 | 10 | 2020-04-08 | Sprint 3
2020-04-13 | Sprint 4 | 4 | 0 | 15 | 2020-04-15 | Sprint 4
2020-04-27 | Sprint 5 | 5 | 0 | -15 | 2020-04-22 | Sprint 5
2020-05-11 | Sprint 6 | 6 | 0 | 15 | 2020-04-29 | Sprint 6
Formulas:
Date adjusted = [Date adjusted, row below]-7
Date adjusted = [Date adjusted, row above]+7
DATE = [DATE, row above]+14

## Sprint Backlog & Burn Charts
Sprint Backlog | [18 empty] | Sprint# | Task#
Sprint Start Date: 1 Feb 19 |  | Sprint End Date: 15 Feb 19 |  | 1 | Task Points | Story Points Progress | [12 empty] | 1 | S01 | S02 | S07
Backlog ID | Tasks |  | Status | Assigned to | Day 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Completed Points | Remaining Points |  | 2 | S07 | S08 | S11
S01 | Manager Application |  | Completed | Team | 22 | 5.5 | 5.5 | 5.5 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 2 | 3 | S04 | S05 | S08 | S09
S02 | Manager Application |  | Completed | Team | 26 | 0 | 0 | 0 | 0 | 5.2 | 5.2 | 5.2 | 5.2 | 5.2 | 0 | 26 |  | 3 | 4 | S05 | S06 | S10
S07 | Driver Application |  | Completed | Team | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 0 | 0 | 9.5 |  | 4 | 5 | S10 | S12 | S14
0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5 | 6 | S13
[5 empty] | Total | 5.5 | 5.5 | 5.5 | 5.5 | 5.2 | 5.2 | 5.2 | 14.7 | 5.2 | 0
|  |  |  | Burndown | 57.5 | 52 | 46.5 | 41 | 35.5 | 30.3 | 25.1 | 19.9 | 5.2 | 2.6645e-15 | 2.6645e-15
|  |  |  | Burn-up | 0 | 5.5 | 11 | 16.5 | 22 | 27.2 | 32.4 | 37.6 | 52.3 | 57.5 | 57.5
Sprint Burn Charts

## Release Burnup
Sprints | 0 | 1 | 2 | 3 | 4 | 5 | 6
Planned |  | 57.5 | 47.1 | 46.4 | 45.5 | 64 | 32 | 0
Cumulative | 0 | 57.5 | 104.6 | 151 | 196.5 | 260.5 | 292.5 | 292.5
Scope | 292.5 | 293 | 293 | 293 | 293 | 293 | 293
Sprint | 0 | 1 | 2 | 3 | 4 | 5 | 6

## Sprint Velocity Chart
Sprint Velocity Chart
Sprint # | Story Points Committed | Story Points Completed | Variance | Sprint End Date | Comments
1 | 57.5 | 57.5 | 0 | 2020-03-13
2 | 47.1 | 47.1 | 0 | 2020-03-27
3 | 46.4 | 46.4 | 0 | 2020-04-12
4 | 45.5 | 36.4 | 9.1 | 2020-04-24
5 | 64 |  | 64 | 2020-05-08
6 | 32 |  | 32 | 2020-05-22
AVG: | 48.75 | 46.85 | 17.5167
About the Sprint Velocity Chart
The Scrum Master updates the Sprint Velocity Chart following each Sprint Review meeting
with the Story Points that were committed, the total Story Points that were accepted as
done by the Product Owner, and the variance between committed and completed.
This information is used in the Sprint Retrospective meeting to assess the team's progress.
It can also be used for release planning to estimate how many more sprints will be needed to
complete the Scrum project.
Formulas:
Sprint End Date = VLOOKUP([Sprint #],'Product Backlog Tasks'!B:T,19,0)

## Iteration Review Status
Product Owner: Cengiz Beslen | Sprint 4 Review | 2020-04-13 |  | 2020-04-24
ScrumMaster: Chau Nguyen |  | 2020-04-23 |  | Status: G
Accomplishments |  | Contingence:
1: Competed user stories S05, S06 and S10. |  | 1: All meeting are converted to online meeting due to COVID-19. 2: All work will be done and shared using cloud services.
2: Groomed Sprint 5 user stories and provided story points. |  | Risks:
3: Completed Sprint 4 Review report |  | Regards to project, None Be safe and work productively during this crises.
4: Completed a Iteration Retrospective report |  | Issues:
5: Completed Epic Progress report |  | None
Next Steps |  | Major Timeline Milestones
1: Groom Sprint 4 user stories. |  | Sprint | Start Date | End Date | Major Decisions or Key Activtives
2: Work on Sprint 4 to complete scheduled work online. |  | Sprint 1 | 2020-03-02 | 2020-03-13 | Based on Product Roadmap
3: Select a time for daily sprint meeting using MS Teams. |  | Sprint 2 | 2020-03-16 | 2020-03-27 | Based on Product Roadmap
|  | Sprint 3 | 2020-03-30 | 2020-04-10 | Based on Product Roadmap
|  | Sprint 4 | 2020-04-13 | 2020-04-24 | Based on Product Roadmap
Formulas:
Start Date = [Start Date, row above]+14
End Date = [Start Date]+11

## Epic Progress (old)
Epic Progress Report
Values below are calculated
Epic | Initial Estimate | Done | In progress | New estimate | New estimate Remaining
Epic 1 | 129 | 65 | 59 | 124 | 0 | e1
Epic 2 | 0 | 0 | 57 | 57 | 0 | e2
Epic 3 | 0 | 0 | 27 | 27 | 0 | e3
Epic 4 | 0 | 0 | 0 | 32 | 32 | e4
Epic 5 | 0 | 0 | 0 | 35 | 35 | e5
| 129 | 65 | 143 | 275 | 67

## Iteration Retrospective
Sprint 4 Retrospectives
No. | Category | Item | Votes | Actions
1 | Good (Keep) | Tester did thoroughly testing and found some defects | 1
2 |  | Developper responded to changes and fixed defects in a timely manner | 1
3 |  | Good Project tracking and monitoring | 2
4 |  | Excellent team calloboration | 3
5 |  | Provided good task edtimation for the project | 1
6 |  | Continuously testing and refactoring | 1
7 | Bad (Drop) | None | 1
8 | Ugly (Confusing) | Current MS team is too slow, need replacement tool for daily meeting | 4 | IT department need to improve MS Teams progression regards to current systems
9 |  | Due to current work from home ordered by government, some tasks are hard to keep up with. | 4 | Aditional training needs to be given for the use of MS Teams

## Epic Progress
Epic Progress Report
Values below are calculated
Epic | Initial Estimate | Done | In progress | New estimate | New estimate Remaining |  | Initial Estimate | [5 empty] | Done |  |  |  |  | In progress
Epic 1 | 129 | 108 | 21 | 129 | 0 | e1 | S01 | S02 | S03 | S04 | S05 | S06 | S01 | S02 | S03 | S04 | S05 |  |  |  | S06
Epic 2 | 61.5 | 48 | 13.5 | 62 | 0.5 | e2 | S07 | S08 | S09 | S10 |  |  | S07 | S08 | S09 |  |  |  |  | S10
Epic 3 | 35 | 15 | 20 | 35 | 0 | e3 | S11 | S12 |  |  |  |  | S11 | [5 empty] | S12
Epic 4 | 32 | 0 | 32 | 32 | 0 | e4 | S13 | [10 empty] | S13
Epic 5 | 35 | 0 | 35 | 35 | 0 | e5 | S14 | [10 empty] | S14
| 292.5 | 171 | 121.5 | 293 | 0.5